## Sheet1
Performance
# | Description | Day Director | Activity Leader/supplier | Start Date | End Date | Start time | end time | Initial contact | Confirmed Attendance | Announced | Cost | Paid | Updates | Status
1 | Outdoor PA system for announcements | JG/AP | Unknown | 2022-06-02 | 2022-06-05 | 10:00 | 21:00 | N | N | N | Unknown | N | 18/02/2022 - Needs to be suitable and powerful for outdoor setting 24/03/22 Spoken to JP for power supply Happy to help. | WIP
2 | Road Closure 1 | Simon Taylor | Craig Willshire at Amey | 2022-06-02 | 2022-06-02 | 10:00 | 23:59 | Y | Y | N | 4423.48 | N | 18/02/2022 - Simon has got quote for Traffic Management, asked for discount and contribution from Persimmon. Angela has applied for closure. | WIP
3 | TOWN CRIER AND THE ‘Oyae’ Announcement | JG/AP | Unknown | 2022-06-02 | 2022-06-02 | 14:00 | 14:30 | N | N | N | Unknown | N | 18/02/2022 - No main Crier at present. Support from Scouts and Weldon Amateur dramatics’ Society. WAD – have their own costumes. Script provided in QPJ pack. Announcement in three places at the same time. | WIP
4 | Fancy Dress Competition | JG/AP | Unknown | 2022-06-02 | 2022-06-02 | 14:30 | 15:30 | N | N | N | Unknown | N | 18/02/2022 - designs from the idea of ‘the Queens Green Canopy'. Recycled outfits designed. Judges and prizes to be sort. | WIP
5 | Parade of decorated Bicycles | JG/AP | Unknown | 2022-06-02 | 2022-06-02 | 15:30 | 16:30 | N | N | N | Unknown | N | 20/02/2022 - (Prize for best, could categorised into size/age). All need to have a bell or horn as they ride the bike on Stamford RD, closed part. Will be lined up against the fence of the Cricket Ground. Need judge and prizes. | WIP
6 | CANCELLED Opening of the play equipment | JG/AP | Unknown | 2022-06-02 | 2022-06-02 | 16:30 | 16:45 | N | N | N | Unknown | N |  | DELETE
7 | Cricket Match | JG/AP | Andy Warren | 2022-06-02 | 2022-06-02 | 17:45 | 20:00 | Y | Y | Y | 0 | - | 18/02/2022 - Arrangements completed | Completed
8 | Choir singing - Deep Roots Tall Trees | JG/AP | Neil Paris | 2022-06-02 | 2022-06-02 | 21.15.00 | 21:45 | Y | N | N | Unknown | N | 24/03/2022 - Choir have asked for 21.15 start. Agreed. Song list to be confirmed Choir = 20 to 30 singers | WIP
9 | Piper | JG/AP | Mark McLaughlan | 2022-06-02 | 2022-06-02 | N | N | Y | N | N | Unknown | N | 24/03/2022 - Peter to contact Mark for time and availability once time is confirmed | WIP
10 | Bugler call to play ‘Majesty’ | JG/AP | Unknown | 2022-06-02 | 2022-06-02 | N | N | N | N | N | Unknown | N | 18/02/2022 - Dick Priem or Kane Taylor to be contacted by Angela | WIP
11 | Lighting of the Beacon | JG/AP | Charlotte Worthington | 2022-06-02 | 2022-06-02 | 21:00 | 21:15 | N | N | N | Unknown | N | 18/02/2022 - Lighting of the Beacon by Charlotte, our local Olympic Gold Medallist, if she can’t make it Mandy Young from Adrenaline Alley will step in. Risk Assessment completed and documented by Darren Melville on 17 February – JG & PD 24/03/22 received form for Mandy if ligthing the beacon. Part completed AP | WIP
12 | National Anthem to be included with a toast to Her Majesty. | JG/AP | Unknown | 2022-06-02 | 2022-06-02 | N | N | N | N | N | Unknown | N |  | WIP
13 | Picnic on the Green with Food stalls | JG/AP | Unknown | 2022-06-02 | 2022-06-02 | N | N | N | N | N | Unknown | N | 24/03/22 JG & AP completed site plan for points 3,14,15 Separate document. Letters to houses around the green and on road closure to be delivered. AP | WIP
14 | Catering Outlets/Vans/Fast Food - Tuckers Catering & Village Kitchen. | JG/AP | Unknown | 2022-06-02 | 2022-06-02 | N | N | N | N | N | Unknown | N | 20/02/2022 -Tuckers Catering & Village Kitchen. Provide own power | WIP
15 | Ice Cream Van | JG/AP | Unknown | 2022-06-02 | 2022-06-02 | N | N | N | N | N | Unknown | N | 18/02/2022 - FREE CONE FOR EVERY CHILD IN THE PARISH – to be published in Parish Magazine (Weldon Wide) to claim a voucher. 24/03/22 JG has confirmed Ice cream Van | WIP
16 | Display of Army Vehicles around the road area of the green | JG/AP | Unknown | 2022-06-02 | 2022-06-02 | N | N | N | N | N | Unknown | N | 18/02/2022 - Dick Priem to investigate. Canon Firing and Fly Pass – Dick Priem discuss with Andy Warren 24/03/2 AW has emailed SC and is looking into, after AP also contacted AW Times TBC | WIP
17 | Bell Ringing | JG/AP/KT | Unknown | 2022-06-03 | 2022-06-03 | 10:45 | 11:00 | N | N | N | Unknown | N | 20/02/2022 - Bell Ringing – discuss with Kane Taylor | WIP
18 | St Mary’s Service of Thanksgiving | JG/AP/KT | Unknown | 2022-06-03 | 2022-06-03 | 11:00 | 12:00 | N | N | N | Unknown | N | 20/02/2022 - St Mary’s Service of Thanksgiving – discuss with KT 23.02.22 Possibly choir singing at St Mary’s – by Queen Eleanor’s Choir. PD to confirmed numbers of choir as 40 to 50 for them to sing up by the organ. 24/03/22 confirm with Sandra displays in the church AP | WIP
19 | Tree planting. | JG/AP | Unknown | 2022-06-03 | 2022-06-03 | 13.00:00 | 13.30.00 | N | N | N | Unknown | N | 20/02/2022 - Walk up after the service to the green. AP suggested a Christmas tree on the green. To establish a yearly tree lighting event at Christmas after very positive reaction to the tree up last Christmas. AP to research type of tree.24/03/22 Site to suggest, on site plan ocument.Plus replace a tree originally planted by the Brownies. Rowan/Magnolia beeen suggested as a cherry tree already on site. | WIP
20 | Big Lunch. | WCC - AW | Unknown | 2022-06-04 | 2022-06-04 | N | N | N | N | N | Unknown | N | 20/02/2022 - Big Lunch. Day for Residents to hold their own Street Parties. WPC will provide an information booklet on this event taken from Official palace documentation supported by Eden project. | WIP
21 | Information Booklet of the Big Lunch | AP | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - WPC will provide an information booklet on this event taken from Official palace documentation supported by Eden project. Circulation date TBD | WIP
22 | Cricket Match. | WCC _AW | Unknown | 2022-06-04 | 2022-06-04 | 12:00 | 19:00 | N | N | N | Unknown | N | 20/02/2022 - Cricket Match. Weldon v Raunds. Open far end of green for a ‘Community Picnic Lunch’ and enjoy a match. | WIP
23 | Section of Stamford Road closed | JG/AP | Unknown | 2022-06-05 | 2022-06-05 | 10:00 | 23:59 | N | N | N | Unknown | N | 20/02/2022 - as per item 2. Simon has got quote for Traffic Management, asked for discount and contribution from Persimmon. Angela has applied for closure. 24/03/22 Agreed only Thursday for road closure. Quote received and agreed. | WIP
24 | REARRANGED> Village Hall open to hold exhibitions | Unknown | Unknown | 2022-06-05 | 2022-06-05 | 13:00 | 16:00 | N | N | N | Unknown | N | 20/02/2022 - Clash of village hall booking to be resolved by Angela Page. 24/03/22 See point 18 | WIP
25 | Platinum Pudding Competition. | JG/AP | Unknown | 2022-06-05 | 2022-06-05 | N | N | N | N | N | Unknown | N | 20/02/2022 - Platinum Pudding Competition. Recipe provided WPC. JG has a judge. Prizes needed – AP/ JG. 24/03/22 Prize sourced. Pudings arrive 12.30pm. JG & Paul Kerfoot(to be asked) to judge.Suggested from recipes and their stories publish a W Recipe Bk to sell. Funds to Youth Grps. | WIP
26 | Display of Village History | JG/AP | Darren Melville | 2022-06-05 | 2022-06-05 | N | N | N | N | N | Unknown | N | 20/02/2022 - Display of Village History – Historic Society. 24/03/22 JG to contact Celia and Peter to support. Prepare a collage. | WIP
27 | Display of Art from WAG | Unknown | Unknown | 2022-06-05 | 2022-06-05 | N | N | N | N | N | Unknown | N | 20/02/2022 - Display of Art from WAG – Art Competition ‘Green Canopy’ for a commission piece to hang somewhere in the Village. JG/AP prizes and judge. 24/03/22 JG had no clear response form WAG AP will try to attend a Thursday session 1.30pm to discuss. | WIP
28 | Time Capsule Display | Unknown | Janet Gibson | 2022-06-05 | 2022-06-05 | N | N | N | N | N | Unknown | N | 20/02/2022 - A Display of progress for our Time Capsule. | WIP
29 | Cricket Club match | Unknown | Andy Warren | 2022-06-05 | 2022-06-05 | 14:30 | 20:00 | N | N | N | Unknown | N | 20/02/2022 -Cricket Club match – new game, T20 style. | WIP
30 | Best Decorated House | Unknown | Unknown | 2022-06-05 | 2022-06-05 | N | N | N | N | N | Unknown | N | 20/02/2022 - Competition for best Decorated House in the Parish, 1st, 2nd and 3rd Announced. Article in ‘Weldon Wide’ for households to enter. Residents receive a map of houses to judge and post their entries and winner announced. 24/03/22 In WW to enter photosof decorated houses. Make a collage for WW and Time Capsule. | WIP
31 | CHANGED to Point 30 Map of best decorated houses | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - Residents receive a map of houses to judge and post their entries and winner announced. | WIP
32 | DELETE Opening of the play equipment, | Unknown | Unknown | 2022-06-05 | 2022-06-05 | N | N | N | N | N | Unknown | N | 20/02/2022 - Opening of the play equipment, see June 2nd | WIP
33 | The PLATIUNUM Cup | Unknown | Andy Warren | 2022-06-05 | 2022-06-05 | N | N | N | N | N | Unknown | N | 20/02/2022 - AP suggested starting the yearly event for the cricket club to play for ‘The PLATIUNUM Cup'. Play in June so can coincides with centenary event of cricket club. AW to confirm. 24/03/22 AW confirmed Match and will source the trophy. P Kerfoot to present. | WIP
34 | Final lighting of the Beacon | Unknown | AP request. - Group considered other Village members | 2022-06-05 | 2022-06-05 | 20:30 | N | N | N | N | Unknown | N | 20/02/2022 - Final lighting of our Beacon - Chair of WPC, Angela Page. Short speak and National Anthem sung. Does this need a choir? 24/03/22 AP felt other village members TBC for lighting beacon | WIP
35 | Gandy Field Garden | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - please see document of draft design and information. JG purchased a metal sculpture for the garden. AP to ask U&C to pick various items left by builders after works to support the Bug Hotel. Talking to the Youth group, schools, and Knit & Natter Grp to support Gandy Field and Yarn Bombing. AP/JG 24/03/22 AP visited /spoken to Primary schools for support. All agreed. Youth grp also suporting AP will do a visit in April. AP in discussions with BAM for volunteers and materials. Finance agreed using the Play equipment wood for the sensory project. | WIP
36 | Weldon Village Sign | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - JG in discussion with designer. To be updated. Can this be illuminated? | WIP
37 | Yarn Bombing | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022- -Talking to the Youth group, schools, and Knit & Natter Grp to support Gandy Field and Yarn Bombing. AP/JG. Post Office to get permission for yarn bombing boxes. AP 24/03/22 permission agreed by Post office. | WIP
38 | Toilet's | Simon Taylor | Unknown | 2022-06-02 | 2022-06-05 | 9:00 | 23:59 | N | N | N | Unknown | N | 20/02/2022 - Provisiion and sponsorship for Porta Loos – Simon Taylor. 24/03/22 request toilets to be sited by the Round house. | WIP
39 | Grant Applications | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - Grant applications – AP & PD Small grant applied for awaiting decision need date for this | WIP
40 | Allotment holders competition | Unknown | Janet Gibson | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - Allotment holders – growing and prizes JG | WIP
41 | Photographer | Unknown | Martin Finnerty | 2022-06-02 | 2022-06-05 | 9:00 | 23:59 | N | N | N | Unknown | N | 20/02/2022 - Photographs will be taken over the 4 days by our resident photographer Martin Finnerty, this monumental occasion will be archived in our Time Capsule | WIP
42 | British Legion | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - British Legion – discuss involvement . 24/03/22 see point 16 The idea of buying large poppies for the GF and ask people to sponsor them was approved. | WIP
43 | High Street Businesses/Public Houses/Shops | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - High Street Businesses/Public Houses/Shops – JG & AP. Full list to be added to this action log | WIP
44 | Project Organisation | Unknown | Unknown | 2022-02-20 | N | N | N | N | N | N | Unknown | N | 20/02/2022 - PR remarked on getting the team wider and involvement of activities. Need to establish who will help on the any or all of the days for Weldon’s events to mark the celebration and community spirit for all. | WIP
45 | local Village Hero | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - Suggested looking at Honouring a local Village Hero Award to a nominated person, could be advertised for nominations in Weldon Wide. TBC | WIP
46 | WPC Facebook business Page | Peter Dowsett | Tom Clay, Breakthrough Communications | 2022-03-07 | Cont. | 0:00 | 0:00 | Y | Y | Y | 1314 | Y | 20/02/2022 - New WPC FaceBook Page to be launched and lead with QPJ. Angela and Janet have provided first posts. Peter has collected required content. | Completed
47 | The George PH | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - Simon Taylor to help with initial contact | WIP
48 | Bug boxes & bird Box workshops | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - JG & AP have meet with U&C to use the Community Hub room for workshops of crafters. Twice monthly. Bug boxes & bird Boxes – summer outside TBC | WIP