## Sheet1
Issue 14/04/2022 Item # | Priority for next Meeting | Date Raised | Action | Who | Target Completion Date | Update Comments | Action Status | Completion date
2 | P1 | 2021 | Close Kettering Rd or agree alternative | Simon Taylor |  | 14/04/2022 - Meetings being arranged with NNC to review community consultation feedback and revise off-site trafic calming for Weldon Village 10/03/2022 - NNC Highways have reverted to Persimmon. Simon to liaise with Dan at Persimmon 09/02/2022 Simon is chasing this constantly. NNC Highways consider this to be low in their priorities - Letter of challenge proposed. 12/01/2022; Chase NNC Highways for decision on closure | Simon
21 | P1 | 2021 | Respond to NNC Highways letter (Author was Sarah Barnwell and 3x versions were sent to WPC, MP and PRD) | Simon Taylor Peter Dowsett Angela Page Mike Page |  | 14/04/2022 - Need to work with the Ward Councillors to create a united front. David Sims proposed a newspaper article to raise the pressure on NNC Highways 10/03/2022 - Email received from Graeme Kane that Angela has produced draft response for, awaits approval by Cllrs. 09/02/2022 WPC Ch. has written to senior managers at NNC, Tom Pursglove, DfT etc. As has PRD. Mike Page to raise at Rural Forum. 12/01/2022: Simon and peter to meet to draft response. Simon is already liaising with Persimmon | Angela
23 | P1 | 2021 | Weldon Parish 20mph zone (Was - Corby Rd formal 20mph application) | Simon Taylor Peter Dowsett |  | 14/04/2022 - Awaiting response from NNC Highways. Peter sent email to ward Clls asking for their support 10/03/2022 - Expert advice obtained from Rod King MBE. Appeal type response sent back on 16 Feb 2022 requesting all Weldon to become 20mph zone. Simon to chase NNC Highways. 09/02/2022 Rejected. Challenge to be constructed by PRD who proposes going for whole parish except A43. 12/01/2022; Chase NNC Highways for response | Simon
13 | P1 | 2021 | WELDON PATHS & PAVEMENTS 1st Item: Church Street footpath | Simon Taylor Colin Shepard |  | 10/03/2022 - Developers have go-ahead from NNC planning and this includes full length footpath for Church Street. Simon to chase. 09/02/2022 Simon had onsite meeting with C3 Construction who confirmed this is feasible from Oundle Rd to footpath HF13 and potentially to the Church. Proposed next step is to bid for £1k from WPC for preparatory survey, engineering drawings and estimate of cost (Arcom or similar). BUT before this WPC should get confirmation from NNC Highways that they are unable to do anything!!! 12/01/2022; Documented here... https://weldonparishcouncil.files.wordpress.com/2021/11/weldon-parish-paths-and-pavements-ver1-2021_0408-3.pdf | Simon
16 | P1 | 2021 | A43 pedestrian crossing | Mike Page |  | 14/04/2022 - Awaiting approval by NNC Highways 10/03/2022 - Simon has written formal letter of complaint about NNC employee conduct. Simon to chase. 09/02/2022 Mike to continue work with Arcom and NNC Highways to gain approval. 12/01/2022; NNC Highways have raised technical challenges and response has been provided. Chase NNC Highways for approval | Simon
1 | P2 | 2021 | Buy 2 new speed VAS signs and install at agreed locations | Simon Taylor |  | 14/04/2022 - Installation anticipated by the end of April 2022 10/03/2022 - Delivery immanent and to be installed at High Street and Corby Road. Also move existing sign on Stamford Road nearer to zebra crossing. 09/02/2022 Purchase order placed Awaiting delivery. Potential roads for install: Corby Rd, Kettering Rd at previous site, Church Street. 12/01/2022; Update needed for next meeting | Simon
15 | P2 | 2021 | Deploy WPC 7.5t advisory signs | Simon Taylor |  | 14/04/2022 - 7.5t signs have been scouped up by the traffic management company that dealt with the Persimmon roundabout closure. retrieve and redeploy 10/03/2022 - 7.5t signs deployed. Early indications that this is reducing HGVs in Weldon Village substantially. Peter to Liaise with Nigel to have them moved to the centre island and adjacent verge. 09/02/2022 Signs with Nigel to deploy ASAP. NB Ensure there are sufficient sand bags for stability of these tall A frames. 12/01/2022; Agreed to deploy at end of road closure for roundabout remedials | Simon
17 | P2 | 2021 | The George PH parking by the zebra | Peter Dowsett Simon Taylor |  | 14/04/2022 - Simon to progress with Peter at George PH this week 10/03/2022 - Carried forward. 09/02/2022 Simon to progress with Peter at George PH 12/01/2022 Peter discussed with Peter Wynne the publican. | Simon
26 | P2 | 2021 | a. Progress changes to road signs associated with the Weldon Relief Road b. Re-route X4 bus from Oundle Road to the Weldon Relief Road c. 7.5t limits to Oundle Road and Stamford Road |  |  | 14/04/2022 - Simon to discuss with Dan at Persimmon 10/03/2022 - Items 4,5 and 6 merged to this entry. Simon to discuss with Dan at Persimmon 09/02/2022 Mike to investigate the possibility to engage a competent advisor with Director at Arcom 12/01/2022; work with Persimmon to progress | Simon
7 | P2 | 2021 | Double Yellow Lines | Angela Page Mike Page |  | 14/04/2022 - Apology email received from Sarah Barnwell. DLYs doc to be sent to WPC Clerk 10/03/2022 - Carried forward 09/02/2022 Mike to investigate the possibility to engage a competent advisor with Director at Arcom 12/01/2022; Chase Sarah Barnwell for update | Mike
8 | P2 | 2021 | NNC response to Planters in road | Simon Taylor Mike Page |  | 14/04/2022 - Discussed at meeting and email sent to Ward Cllrs with request for help by Peter 10/03/2022 - Simon to chase NNC Highways for response to email dated September 2021?? Also to provide AutoCAD design. 09/02/2022 Mike to investigate the possibility to engage a competent advisor with Director at Arcom 12/01/2022; Chase NNC Highways for response on new submission https://weldonparishcouncil.files.wordpress.com/2021/11/wpc-parking-pedestrians-and-planters-2021_0928.pdf | Simon
11 | P2 | 2021 | 20s Plenty project | Peter Dowsett Angela Page Graham Stray Simon Taylor |  | 10/03/2022 - Peter to work with Nigel to deploy remaining signs. Also get quote for school lamppost campaign 09/02/2022 Graham to order 20sPlenty Banners for schools and care home. 20sPlenty A frames to be deployed ASAP, Simon to lead with Nigel. 12/01/2022; Convert A frame signs to 20s Plenty and increase number to 8. Purchase Request required for the finance meeting. Graham to buy 2x banners for school. Colin to collect wheelie bin stickers from Sue and enlist dog walkers and known villagers. Peter to arrange meeting with CofE school. | Peter
18 | P2 | 2021 | Speed-watch | Graham Stray |  | 14/04/2022 - Kevin Watt to be added to vollunteer list 09/02/2022 March training x6 volunteers. All activities are covered by Police insurance. 27/01/2022 Northants Police Safer Roads Team have confirmed training for 2022 should be in March and I have 6 x people who have signed up for it. As soon as I get the actual training dates I’ll let you know and the subsequent monitoring sessions throughout the Parish. Currently only the 3 x sites previously authorised by the Police within Weldon Village can be used for the sessions but I’m hoping that following the completion of the speed limit signs to the access roads for PHP we will be able to get authorised sites there. The police have confirmed that un-adopted roads, so all of PHP currently, can be authorised providing the correct speed limit signs are up and street lighting is to the correct standards. Urban & Civic have been asked to confirm the signs and lighting items are OK. | Graham
10 | P3 | 2021 | Public Transport growth plan | Mike Page |  | 0/03/2022 - Carried forward 09/02/2022 Mike to formulate response to NNC for WPC. Noted that bus to Stamford was discontinued a generation ago and no new services proposed for the massive growth in community. What is the future of bus travel? | Mike
24 | P3 | 2022-01-12 | Positive engagement and working relationship with NNC ward councillors and leadership team (Jason Smithers and Graham Lawson) | Angela Page Sue Cook |  | 14/04/2022 - The meeting welcomed David Simms and Kevin Watt 10/03/2022 - Carried forward 09/02/2022 Sue to research role of Rural Councillors. Potential to discuss with Jason Smithers. 12/01/2022; Sue to write to ward councillor regarding absence and no apology | Angela
25 | P3 | 2022-02-09 | Verge encroaching on Oundle Rd footpath. Colin has done an exploratory dig and found 2m wide pavements under the verge and boundary to the Rookery! | Colin Shepard Peter Dowsett |  | 14/04/2022 - Discussed terrible default 26 week service time from NNC Highways with ward Cllrs 10/03/2022 - Simon to contact NNC Highways (Ben Wright) to accelerate from 26 weeks! 09/02/2022 PRD has raised on FixMyStreet. Support photos to be added | Simon
27 | P3 | 2022-03-10 | Verge encroaching on Kettering Rd footpath. | Peter Dowsett |  | 14/04/2022 - Discussed terrible default 26 week service time from NNC Highways with ward Cllrs 10/03/2022 - Raised on FixMyStreet | Peter
19 | P3 | 2021 | Bypass campaign | Angela Page |  | 14/04/2022 Signature is now at 266 09/02/2022 Supported at WPC full council | Ongoing
3 | P999 | 2021 | Find status and date for Oundle Road roundabout rework | Simon Taylor |  | 14/04/2022 - Noted the two weeks of bliss throughout the whole village as the rat-run was tamed for the duration of the roundabout closure 10/03/2022 - Carried forward 09/02/2022 Rescheduled to 4 to 15 April due to NNC Highways paperwork issue 12/01/2022; Confirmed as 24 Jan to 4 Feb. Closure sign required for Oundle Rd by war memorial (also Stamford Rd?) | Closed
22 | P999 | 2021 | QPJ Stamford Rd closure | Angela Page Janet Gibson | 2022-05-01 | 10/03/2022 - Cheaper options being considered 09/02/2022 Application made by Angela 12/01/2022; Could be made easy by government announcement | Closed
4 | P999 | 2021 | Progress changes to road signs associated with the Weldon Relief Road | Simon Taylor Mike Page |  | 10/03/2022 - Merged into item 26 09/02/2022 Mike to investigate the possibility to engage a competent advisor with Director at Arcom 12/01/2022; work with Persimmon to progress | Closed
5 | P999 | 2021 | Re-route X4 bus from Oundle Road to the Weldon Relief Road | Simon Taylor Mike Page |  | 10/03/2022 - Merged into item 26 09/02/2022 Mike to investigate the possibility to engage a competent advisor with Director at Arcom 12/01/2022; work with Persimmon to progress | Closed
6 | P999 | 2021 | 7.5t limits to Oundle Road and Stamford Road | Simon Taylor Mike Page |  | 10/03/2022 - Merged into item 26 09/02/2022 Mike to investigate the possibility to engage a competent advisor with Director at Arcom 12/01/2022; work with Persimmon to progress | Closed
20 | P999 | 2021 | Remove objection to Persimmon phase 3 | Simon Taylor |  | 09/02/2022 NNC Planning have removed the objection to Persimmon Ph 3 (presumably because the Weldon Relief Road is open now). NNC Highways continue to obstruct items 4, 5 and 6 because the Weldon Relief Road is not open for use in the road network! Proposed that Simon contacts NNC Planning to confirm why they have removed objection. WPC to challenge as necessary. 12/01/2022; Dependent on 7.5t, X4 bus and offsite road sign changes | Closed
12 | P999 | 2021 | CofE School parking and walking bus | Peter Dowsett |  | 10/03/2022 - Meetings held with Judith Spear. Actions in place 09/02/2022 Zoom meeting held with Judith (school governor) 12/01/2022; Email sent to Judith on 11 January 2022 | Closed
9 | P999 | 2021 | Church Street HGV video cameras | Peter Dowsett |  | 09/02/2022 NNC Highways unable to help with video equipment or enforcement 12/01/2022; Awaiting response from Sarah Barnwell | Closed
14 | P999 | 2021 | Highways advisory 20 trial | Angela Page Peter Dowsett |  | 12/01/2022 Signs are too small and low contrast to be noticed. No further action. Respond to Sarah Barnwell if requested. | Closed