## QPJ
Performance
Item Number | Description | Day Director | Activity Leader/supplier | Start Date | End Date | Start time | End time | Initial contact | Confirmed Attendance | Announced | Cost | Paid | Updates | Status
60 | Risks Key Person Risk Angela Page Janet Gibson |  |  | N | N | N | N | N | N | N | N | N
59 | Site Pre-meet (Dress rehearsal) | Janet Gibson | Janet Gibson | N | N | N | N | N | N | N | N | N | 21/04/2022 - new row added
57 | Advertising Notice Boards Face Book WW Magazine Cricket Club Leaflets Schools leaflet | Angela Page | Angela Page | N | N | N | N | N | N | N | N | N | 21/04/2022 - new row added | Angela Page
56 | Memorabilia | Angela Page | Angela Page | N | N | N | N | N | N | N | N | N | 21/04/2022 - new row added | Angela Page
55 | Prizes Beautician - Lisa Smith Platinum Trophy Londis? | Janet Gibson | Janet Gibson | N | N | N | N | N | N | N | N | N | 21/04/2022 - List to be circulated | Janet Gibson
54 | Entry signs to Gandy Field | Janet Gibson | Gaye Hood-Henry | 2022-12-31 | 2022-12-31 | 0:00 | 0:00 | Y | Y | N | Unknown |  | 21/04/2022 - Janet to confirm arrangements | Janet Gibson
6 | CANCELLED - Opening of the play equipment | Angela Page Janet Gibson | Unknown | 2022-06-02 | 2022-06-02 | 16:30 | 16:45 | N | N | N | Unknown | N | 02/04/2022 - Cancelled 18/02/2022 - possibly here so can be in use on Saturday 4th for ‘Community Picnic Lunch’ | Completed
7 | Cricket Match | Angela Page Janet Gibson | Andy Warren | 2022-06-02 | 2022-06-02 | 17:30 | 20:00 | Y | Y | Y | None | - | 04/03/2022 - Start time delayed to 17:30 18/02/2022 - Arrangements completed | Completed
8 | Choir singing - Deep Roots Tall Trees (DRTT) | Angela Page Janet Gibson | Neil Paris | 2022-06-02 | 2022-06-02 | 21:00 | 21:45 | Y | Y | N | 250 | N | 21/04/2022 - to bring own PA system discussed safety certificate 02/04/2022 - Choir have asked for 21:15 start and this was agreed 04/03/2022 - Plan to dress in red, white and blue. Family and friends to be invited. Payment to be reviewed once budget total is clear. Neil to confirm times and song list together with link to Spotify etc. First verse of national anthem included 18/02/2022 - Choir have been told 21:15 to 22:00 so time needs to be confirmed. Song list to be confirmed Choir = 20 to 30 singers | Completed
9 | Piper | Angela Page Janet Gibson | Mark McLaughlan 07974 625 226 | 2022-06-02 | 2022-06-02 | 20:00 | 20:30 | Y | Y | N | 180 | N | 02/04/2022 - Peter has confirmed with Mark that he will be our Piper. Mark is learning the piece that has ben composed for the QPJ and is flexible to play other stuff. Mark will need to leave 20:30ish to go to next engagement. 04/03/2022 - Left message on voicemail 18/02/2022 - Peter to contact Mark for time and availability once time is confirmed | Completed
53 | Create site plan for Village Green | Angela Page Janet Gibson | Angela Page Janet Gibson | 2022-03-04 | 2022-06-01 | 0:00 | 11:59 | Y | Y | N | None | - | 21/04/2022 - Plan to be circulated 04/03/2022 - Janet Gibson and Angela page to visit site and draft site plan | Angela Page
11 | Lighting of the Beacon | Angela Page Janet Gibson | Charlotte Worthington | 2022-06-02 | 2022-06-02 | 21:00 | 21:15 | Y | Y | Y | 300 | N | 02/04/2022 - Received form for Mandy if lighting the beacon. Part completed by Angela 18/02/2022 - Lighting of the Beacon by Charlotte, our local Olympic Gold Medallist, if she can’t make it Mandy Young from Adrenaline Alley will step in. Risk Assessment completed and documented by Darren Melville on 17 February – JG & PD | Completed
50 | International Group CIC - Corby Can | Angela Page Janet Gibson | Danielle Parry | 2022-06-02 | 2022-06-02 | 16:30 | 18:30 | Y | Y | N | None | - | 21/04/2022 add art for the church 04/03/2022 - 7 peeps, Traditional costume, E. European, gymnastics, dance, needs PA, to enter fancy dress competition & bicycle competition, Tattoos, needs Gazebo for workshops, write article for Weldon Wide | Angela Page
49 | Prepare Website page for QPJ and content for activities and entries. | Angela Page Sue Cook | Angela Sue Cook | 2022-03-04 | 2022-12-31 | 0:00 | 11:59 | Y | Y | Y | None | - | 21/04/2022 - Angela to write up with Sue 04/03/2022 - Initial drafts produced. Angela to work on this next week | Angela Page
48 | Bug boxes & bird Box workshops | Angela Page Janet Gibson | Angela Page Janet Gibson | 2022-04-01 | 2022-12-31 | 0:00 | 0:00 | Y | Y | N | Unknown | N | 21/04/2022 Information given to youth groups 20/02/2022 - JG & AP have meet with U&C to use the Community Hub room for workshops of crafters. Twice monthly. Bug boxes & bird Boxes – summer outside TBC | Angela Page
47 | The George PH | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 21/04/2022 - Session arranged with Angela and Janet 20/02/2022 - Simon Taylor to help with initial contact | Simon Taylor
43 | High Street Businesses/Public Houses/Shops | Janet Gibson | Peter the publican! | 2022-06-02 | 2022-06-05 | 10:00 | 23:59 | N | N | N | Unknown | N | 21/04/2022 - Need to confirm which businesses are doing what 20/02/2022 - High Street Businesses/Public Houses/Shops – JG & AP. Full list to be added to this action log | Janet Gibson
42 | British Legion | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 02/04/2022 - See item 16 (is this a duplicate?). The idea of buying large poppies for the Gandy Field and ask people to sponsor them was approved 20/02/2022 - British Legion – discuss involvement | Angela Page
40 | Allotment holders competition | Janet Gibson Angela Page | Janet Gibson | 2022-09-30 | 2022-09-30 | 23:59 | 23:59 | Y | N | N | Unknown | N | 20/02/2022 - Allotment holders – growing and prizes JG | Janet Gibson
39 | Grant Applications | Angela Page | Angela | 2022-12-31 | 2022-12-31 | 0:00 | 23:59 | Y | N | N | Unknown | N | 20/02/2022 - Grant applications – AP & PD Small grant applied for awaiting decision need date for this | Angela Page
20 | Big Lunch. | Angela Page | Rochelle Mathieson | 2022-06-04 | 2022-06-04 | 12:00 | 18:00 | Y | Y | Y | 0 | N | 04/03/2022 - JD Breakfast House role TBC 20/02/2022 - Big Lunch. Day for Residents to hold their own Street Parties. WPC will provide an information booklet on this event taken from Official palace documentation supported by Eden project. | Completed
21 | Information Booklet of the Big Lunch | Angela Page | Angela Page | 2022-04-21 | 2022-04-21 | 0:00 | 0:00 | Y | Y | N | 0 | N | 21/04/2022 - now being provided by website 20/02/2022 - WPC will provide an information booklet on this event taken from Official palace documentation supported by Eden project. Circulation date TBD | Completed
22 | Cricket Match. | Rochelle Mathieson | Rochelle Mathieson | 2022-06-04 | 2022-06-04 | 12:00 | 19:00 | Y | Y | Y | 0 | - | 04/03/2022 - Cricket club planning Play, picknic, Pimms. Order Picnic box in advance. TBC. 20/02/2022 - Cricket Match. Weldon v Raunds. Open far end of green for a ‘Community Picnic Lunch’ and enjoy a match. | Completed
23 | CANCELLED - Road closure 2. Section of Stamford Road closed | Janet Gibson Angela Page |  | 2022-06-05 | 2022-06-05 | 10:00 | 23:59 | Y | N | N | Unknown | N | 02/04/2022 - Cancelled as road closure is for Thursday 2 June only 04/03/2022 - Angela investigating DIY road closure using Scouts and historic military vehicles. Three quotes required if £5k. Sue and Angela to contact Simon Green to investigate other options 20/02/2022 - as per item 2. Simon has got quote for Traffic Management, asked for discount and contribution from Persimmon. Angela has applied for closure. | Completed
38 | Toilet's | Simon Taylor | Persimmon | 2022-06-02 | 2022-06-05 | 9:00 | 23:59 | Y | Y | Y | 0 | N | 21/04/2022 - Clean and maintain 02/04/2022 - Toilets to be sited by the roundhouse 04/03/2022 - Location TBD could be by the style on the cricket pitch 20/02/2022 - Provision and sponsorship for Porta Loos – Simon Taylor | Angela Page
37 | Yarn Bombing and Bunting | Janet Gibson Angela Page | Janet Gibson Angela Page | 2022-05-16 | 2022-05-22 | 0:01 | 23:59 | Y | Y | Y | 230 | N | 21/04/2022 - CIC to join this activity 02/04/2022 - Post office permission given 20/02/2022- -Talking to the Youth group, schools, and Knit & Natter Grp to support Gandy Field and Yarn Bombing. AP/JG. Post Office to get permission for yarn bombing boxes. AP | Angela Page
36 | Weldon Village Sign | Jane Gibson | Blackforge | 2022-12-31 | 2022-12-31 | 23:59 | 23:59 | Y | N | N | Unknown | N | 21/04/2022 - Needs full council approval 20/02/2022 - JG in discussion with designer. To be updated. Can this be illuminated? | Janet Gibson
35 | Gandy Field Garden | Janet Gibson Angela Page | Janet Gibson Angela Page | 2022-12-31 | 2022-12-31 | 23:59 | 23:59 | Y | Y | Y | 0 | N | 21/04/2022 - £150 Wickes voucher and BAM to provide volunteer days and equipment 02/04/2022 - Angela has visited and spoken to the Primary Schools for support. All agreed. Youth group also supporting. Angela will visit in April. Angela is also in discussion with BAM for volunteers and materials. Finance agreed using the play equipment wood in the sensory garden project. 20/02/2022 - please see document of draft design and information. JG purchased a metal sculpture for the garden. AP to ask U&C to pick various items left by builders after works to support the Bug Hotel. Talking to the Youth group, schools, and Knit & Natter Grp to support Gandy Field and Yarn Bombing. AP/JG | Angela Page
34 | Final lighting of the Beacon | Janet Gibson Angela Page | Angela Page | 2022-06-05 | 2022-06-05 | 20:30 | 22:00 | N | N | N | Unknown | N | 21/04/2022 - Janet to contact Rita Beatie 02/04/2022 - Angela felt other village members need to be considered for lighting the beacon 20/02/2022 - Final lighting of our Beacon - Chair of WPC, Angela Page. Short speak and National Anthem sung. Does this need a choir? | Janet Gibson
29 | Cricket Club match | Janet Gibson Angela Page | Andy Warren | 2022-06-05 | 2022-06-05 | 14:30 | 20:00 | Y | Y | N | None | - | 21/04/2022 - Confirmed PHP vs Weldon 04/03/2022 - Discussion ongoing could be PHP vs Village + WP? 20/02/2022 -Cricket Club match – new game, T20 style. | Completed
30 | Best Decorated House / garden photos | Janet Gibson Angela Page | Janet Gibson Angela Page | 2022-06-05 | 2022-06-30 | 0:01 | 23:59 | Y | Y | Y | 0 | N | 02/04/2022 - In Weldon Wide Magazine to enter photos of decorated houses. Make a collage for WW Magazine and Time capsule 20/02/2022 - Competition for best Decorated House in the Parish, 1st, 2nd and 3rd Announced. Article in ‘Weldon Wide’ for households to enter. Residents receive a map of houses to judge and post their entries and winner announced. | Completed
31 | CANCELLED - Map of best decorated houses | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 02/04/2022 - In Weldon Wide Magazine to enter photos of decorated houses. Make a collage for WW Magazine and Time capsule 20/02/2022 - Residents receive a map of houses to judge and post their entries and winner announced. | Completed
32 | CANCELLED - Opening of the play equipment, | Janet Gibson Angela Page | Unknown | 2022-06-05 | 2022-06-05 | N | N | N | N | N | Unknown | N | 02/04/2022 - Deleted 20/02/2022 - Opening of the play equipment, see June 2nd | Completed
33 | The PLATIUNUM Cup | Janet Gibson Angela Page | Andy Warren | 2022-06-05 | 2022-06-05 | 14:30 | 17:30 | Y | Y | Y | 150 | N | 21/04/2022 - Possible Sue Singlehurst to present or Paul Kerfoot 02/04/2022 - Match confirmed and Andy will source the trophy. P. Kerfoot to present 20/02/2022 - AP suggested starting the yearly event for the cricket club to play for ‘The PLATIUNUM Cup'. Play in June so can coincides with centenary event of cricket club. AW to confirm. | Andy Warren
28 | Time Capsule Display | Janet Gibson Angela Page | Janet Gibson | 2022-12-31 | 2022-12-31 | 23:59 | 23:59 | Y | Y | N | Unknown | N | 21/04/2022 - Contents to be confirmed from all parts of the parish 20/02/2022 - A Display of progress for our Time Capsule. | Janet Gibson
27 | Display of Art from WAG and CIC group to be held at the Green in a gazebo | Janet Gibson Angela Page | Unknown | 2022-06-05 | 2022-06-05 | N | N | N | N | N | Unknown | N | 21/04/2022 - Janet to chase John Starmer. Daniella to find out if professional artists could contribute. Gazebo needed from Mike Haddock and Kane. 02/04/2022 - Janet had no clear response from WAG. Angela will try to attend a Thursday session at 1:30pm to discuss 20/02/2022 - Display of Art from WAG – Art Competition ‘Green Canopy’ for a commission piece to hang somewhere in the Village. JG/AP prizes and judge. | Janet Gibson
26 | Display of Village History | Janet Gibson Angela Page | Darren Melville | 2022-06-03 | 2022-06-05 | 10:30 | 22:00 | Y | Y | N | Unknown | N | 21/04/2022 - FB post required and PA system and church website and History FB site 02/04/2022 - Janet to contact Celia ???? & Peter ???? to support. Prepare a collage. 20/02/2022 - Display of Village History – Historic Society. | Janet Gibson
25 | Parish Cake Competition. | Janet Gibson Angela Page | Janet Gibson | 2022-06-05 | 2022-06-05 | 10:30 | 17:00 | Y | N | N | Unknown | N | 21/04/2022 - Sue Singlehurst to be added to judges. Judging to be 11:00 with 3X prizes at 12:00 02/04/2022 - Prizes have been sourced. Puddings arrive at 12:30. Janet and Paul Kerfoot (TBC) to judge. Suggested from recipes and their stories publish a W recipe book to sell. Funds to youth groups. 04/03/2022 - Janet to design running order, Prepare on Friday eat on Sunday TBC. Winners cup to be purchased. Photos of preparation, Janet to liaise with Martin Finnerty 20/02/2022 - Platinum Pudding Competition. Recipe provided WPC. JG has a judge. Prizes needed – AP/ JG | Janet Gibson
24 | Church open to hold exhibitions | Janet Gibson Angela Page | Janet Gibson | 2022-06-05 | 2022-06-05 | 13:00 | 16:00 | N | N | N | Unknown | N | 21/04/2022- Church confirmed as venue 02/04/2022 - Angela to confirm with Sandra that displays will be in the church 04/03/2022 - Village hall availability TBC, plan B is the Church or the George PH 20/02/2022 - Clash of village hall booking to be resolved by Angela Page | Angela Page
19 | Tree planting. | Kane Taylor Angela Page | Unknown | 2022-06-03 | 2022-06-03 | 12:15 | 14:30 | N | N | N | Unknown | N | 21/04/2022 - Decide what tree and location and place order. Also determine the person to plant it. 02/04/2022 - Site to suggest, on site plan document. Plus, replace a tree originally planted by the Brownies. Rowan/Magnolia been suggested, as cherry tree already on site. 04/03/2022 - Could be Rockingham Castle donation - Angela to investigate along with sources of donations (Cowthick, BAM etc). The hole needs to be dug in advance by Nigel!!! 20/02/2022 - Walk up after the service to the green. Angela Page suggested a Christmas tree on the green. To establish a yearly tree lighting event at Christmas after very positive reaction to the tree up last Christmas. AP to research type of tree. | Angela Page
18 | St Mary’s Service of Thanksgiving | Kane Taylor Angela Page | Kane Taylor | 2022-06-03 | 2022-06-03 | 11:00 | 12:00 | Y | Y | Y | Unknown | N | 21/04/2022 - Guidance on flower colours 02/04/2022 - Queen Eleanor Choir pulled out due to leader being over committed 02/04/2022 - Angela to confirm with Sandra that displays will be in the church 04/03/2022 - Queen Eleanor Choir confirmed and Jess Hunting to contact Kane Taylor to confirm artistic details and sound equipment requirements. Site visit to be proposed. 20/02/2022 - St Mary’s Service of Thanksgiving – discuss with KT 23.02.22 Possibly choir singing at St Mary’s – by Queen Eleanor’s Choir. PD to confirmed numbers of choir as 40 to 50 for them to sing up by the organ | Angela Page
41 | Photographer | Angela Page Janet Gibson | Martin Finnerty | 2022-06-02 | 2022-06-05 | 9:00 | 23:59 | Y | Y | Y | Unknown | N | 20/02/2022 - Photographs will be taken over the 4 days by our resident photographer Martin Finnerty, this monumental occasion will be archived in our Time Capsule | Completed
17 | Bell Ringing | Kane Taylor Angela Page | Gordon Brown Kane Taylor | 2022-06-03 | 2022-06-03 | 10:45 | 11:00 | Y | N | N | Unknown | N | 21/04/2022 - Angela to confirm 20/02/2022 - Bell Ringing – discuss with Kane Taylor | Kane Taylor
16 | Display of Army Vehicles around the road area of the green | Angela Page Janet Gibson | Trevor from RBL | 2022-06-02 | 2022-06-02 | 12:00 | 22:00 | Y | N | N | None | - | 21/04/2022 - Arrange parade at leaving at 22:00 21/04/2022 - Angela to confirm times 02/04/2022 - Ann Wallington has emailed Sue Cook and is looking into after Angela also contacted Ann Wallington. Times TBC. 04/03/2022 - Initial contact made via Ann Wallington and Dick Priem 18/02/2022 - Dick Priem to investigate. Canon Firing and Fly Past – Dick Priem discuss with Andy Warren | Angela Page
44 | Project Organisation | Peter Dowsett | Peter Dowsett | 2022-02-20 | 2022-12-31 | 0:00 | 0:00 | Y | Y | Y | 0 | N | 21/04/2022 - change order of activity log 20/02/2022 - PRD remarked on getting the team wider and involvement of activities. Need to establish who will help on the any or all of the days for Weldon’s events to mark the celebration and community spirit for all. | Completed
45 | CANCELLED - local Village Hero | Unknown | Unknown | N | N | N | N | N | N | N | Unknown | N | 20/02/2022 - Suggested looking at Honouring a local Village Hero Award to a nominated person, could be advertised for nominations in Weldon Wide. TBC | Completed
46 | Facebook business Page | Peter Dowsett | Tom Clay, Breakthrough Communications | 2022-03-07 | Cont. | 0:00 | 0:00 | Y | Y | Y | 1314 | Y | 04/03/2022 - Email address setup, links to website, staff trained, first posts written, FB page live 20/02/2022 - New WPC Facebook Page to be launched and lead with QPJ. Angela and Janet have provided first posts. Peter has collected required content. | Completed
15 | Ice Cream Van | Angela Page Janet Gibson | Ettore Velluci | 2022-06-02 | 2022-06-02 | 12:00 | 17:00 | Y | Y | N | Unknown | N | 02/04/2022 - Janet has confirmed the ice cream van 04/03/2022 - Angela to write Weldon Wide article with voucher 18/02/2022 - FREE CONE FOR EVERY CHILD IN THE PARISH – to be published in Parish Magazine (Weldon Wide) to claim a voucher. Angela Page to ask MH for name of other ice cream van. | Janet Gibson
14 | Catering Outlets/Vans/Fast Food - Tuckers Catering & Village Kitchen. | Angela Page Janet Gibson | Tuckers & TVK & JD | 2022-06-02 | 2022-06-02 | 12:00 | 22:00 | Y | N | N | Unknown | N | 21/04/2022 - Janet to confirm arrangements 04/03/2022 - Janet to confirm suppliers (food van list) and times 20/02/2022 -Tuckers Catering & Village Kitchen. Provide own power | Janet Gibson
13 | Picnic on the Green with local stalls | Angela Page Janet Gibson | Angela Page Janet Gibson | 2022-06-02 | 2022-06-02 | 12:00 | 22:00 | Y | N | N | Unknown | N | 21/04/2022 - Angela to arrange FB post to find local stalls X8.Possible pitch fee or % of takings 02/04/2022 - Janet and Angela have completed the site plan for Items 3, 14 & 15 on a separate document. Letters to the houses around the Village Green and on the closed road to be created and delivered by Angela 04/03/2022 - Janet to confirm food stall list and village green layout | Angela Page
12 | National Anthem to be included with a toast to Her Majesty. | Angela Page Janet Gibson | DRTT & Angela | 2022-06-02 | 2022-06-02 | 21:45 | 22:00 | Y | Y | N | Unknown | N |  | Angela Page
51 | CANCELLED - Flypast - | Angela Page Janet Gibson | Ann Wallington | 2022-06-02 | 2022-06-02 | N | N | Y | N | N | Unknown | N | 21/04/2022 - Cancelled 04/03/2022 - Flypast TBD or single plane by Tim Webster | Completed
10 | Bugler call to play ‘Majesty’ | Angela Page Janet Gibson | Unknown | 2022-06-02 | 2022-06-02 | 20:00 | 20:30 | N | N | N | Unknown | N | 21/04/2022 - Angela to chase Ann Wallington 04/03/2022 - Ann Wallington to be contacted to confirm cost 18/02/2022 - Dick Priem or Kane Taylor to be contacted by Angela | Angela Page
5 | Parade of decorated Bicycles | Angela Page Janet Gibson | Janet Gibson | 2022-06-02 | 2022-06-02 | 15:30 | 16:30 | Y | Y | N | Unknown | N | 20/02/2022 - (Prize for best, could categorised into size/age). All need to have a bell or horn as they ride the bike on Stamford RD, closed part. Will be lined up against the fence of the Cricket Ground. Need judge and prizes. | Angela Page
4 | Fancy Dress Competition | Angela Page Janet Gibson | Cathy Finnerty | 2022-06-02 | 2022-06-02 | 14:30 | 15:30 | N | N | N | Unknown | N | 21/04/2022 - Angela to contact Cathy 18/02/2022 - designs from the idea of ‘the Queens Green Canopy'. Recycled outfits designed. Judges and prizes to be sorted. | Angela Page
3 | TOWN CRIER AND THE ‘Oyae’ Announcement | Angela Page Janet Gibson | Unknown | 2022-06-02 | 2022-06-02 | 14:00 | 14:30 | N | N | N | Unknown | N | 21/04/2022 - Jan to email Megan Jones. 07733527426 18/02/2022 - No main Crier at present. Support from Scouts and Weldon Amateur dramatics’ Society. WAD – have their own costumes. Script provided in QPJ pack. Announcement in three places at the same time. | Angela Page
2 | Road Closure 1 | Simon Taylor | Craig Willshire at Amey | 2022-06-02 | 2022-06-02 | 10:00 | 23:59 | Y | Y | N | 2171.68 | N | 04/03/2022 - Angela investigating DIY road closure using Scouts and historic military vehicles. Three quotes required if £5k. Sue and Angela to contact Simon Green to investigate other options 18/02/2022 - Simon has got quote for Traffic Management, asked for discount and contribution from Persimmon. Angela has applied for closure. | Simon Taylor
1 | Outdoor PA system for announcements | Angela Page Janet Gibson | Unknown | 2022-06-02 | 2022-06-05 | 10:00 | 21:00 | Y | N | N | Unknown | N | 21/04/2022 - Check with Ann Wallington. A J Matteson to be contacted for safety assessment M 07966390864 by Jan 02/04/2022 - Spoken to Joannie Perkins for mains supply, she is happy to help. 04/03/2022 - Ann Wallington contacted and PA available, possible mains power from Jeanie, must have RCD at indoor supply socket, 18/02/2022 - Needs to be suitable and powerful for outdoor setting | Angela Page
0 | Total cost | [9 empty] | 0 |  | 25/04/2022 - Log Updated 02/04/2022 - Log updated 04/03/2022 - Budget £25,000

## Gandy Garden
Item # | Activity | Members | Research & information | Begin date | Meeting Agreed | Resources | Finish date | Cost | Update
0 | Total Cost | [6 empty] | 0
1 | Design garden | Janet Gibson Angela Page | RHS, Woodland trust | 2022-01-01 | N |  | N | - | 04/03/2022 - Arrange site meeting oncluding Colin Shepard
2 | Inform neighbours | Angela Page | Letters/visit | 2022-03-01 | N |  | N | -
3 | Prepare garden and landscape | Janet Gibson Workgroup | Plan section by section. Mark off area. | Unknown | N | Nigel Cox Youth Group and volunteers Digger Paul - 07818057105 Some materials U&C/allotment | N | N | 04/03/2022 - Ross Wallace for landscape
4 | Seed Planting event | Primary Schools x2 Youth Group | Prepare sheets on sowing seeds by recycling items. | 2022-03-01 | N |  | N | N | AP discuss with 2 primary schools for planting seeds. Include youth grp.
5 | Tree planting event | Workgroup | Woodland Trust | Unknown | N | Woodlant Trust tree pack delivered Feb/March Group to agree placing of plants. Could be about the village or for residents | N | N | 04/03/2022 - Gary Chisholm has fir trees
6 | Bug Hotel | Workgroup | Designed. Request for materials for residents | Unknown | N | several designs placed around the gradens | N | N
7 | Instal the Furniture | Workgroup | Free items, items form residents, reclaim centres. | Unknown | N | Prepare sleepers bench. Slabs for pathway and patio areas. | N | N
8 | Plant the Plants | Workgroup | Plants to support birds, bees and butterflies plus the sensory element. | 2022-02-01 | N | Lavander | N | N
9