WELDON IN BLOOM MINUTES 26TH FEBRUARY 2024

WIB.810 Apologies from Angela.

Attendees: Sharon,Andy,Peter,John,Katie,Colin,Jane,Caroline.

WIB.811 No declarations of interest submitted.

WIB.812 Minutes approved from the meeting held on 22nd January 2024.

WIB.813 No new attendees.

WIB.814 The posters for the competitions have been placed in a couple of the notice boards. But it was agreed that the more places these could be placed the better. A double page spread regarding Weldon In Bloom, will be in the next magazine with the competition details on the back page. Jane also agreed to include details in the next Weldon School’s Newsletter. Jane would also try to contact Alison Prattis at CBA with the information. A letter drop was also suggested approximately a month after the magazine, to keep the momentum going as not everyone reads this publication. Caroline was more than happy to help with this. Colin also confirmed that Simon Green will be providing the prizes with a preliminary suggestion of £75 for first place and 2x£25 for runners up.

WIB.815 Caroline,Katie and Jane are to organise a date to begin the preparation for the brochure. Peter was going to look for old photos of the Gandy Field to show how it looked in the past.

WIB.816 Colin handed out a list of tasks for the next month. Some of the jobs included the following. More places were needed to sow the seeds needed for the various displays. Andy was more than happy for the committee to use his Poly Tunnel on the allotment, once it has been repaired. Caroline offered Harry’s services to help with this. Andy to contact Caroline when a suitable day arises. A litter pick is to be organised to try and keep on top of this before judging. Colin to locate the equipment needed for this. Now that the owner of the Londis has been in for a while, Colin will make contact to discuss if improvements could be made to the exterior. Colin will also complete the application needed to enter the Village in Bloom competition.

WIB.817 Community Payback is still working well. Jobs that are ongoing are painting the planters and railings. It was asked if the payback team could be used for litter picking. Apparently, this is something they are unable to do.

WIB.818 Improvements to the wooden planters (ie painting). This is covered in 817.

WIB.819 All celebrations for D-Day are to take part on the village green on Thursday 6th June, so we now have a deadline for the area. Colin is to chase Simon Taylor for the sandbags/sand. It was agreed that the Tank should be left as it is, as it would add to the theme of war with the holes etc. The sandbags and planting would help hide some of its defects. Andy updated the committee on the work to be carried out on the Boules area. The planting scheme is yet to be finalised, but again it would reflect the celebrations.

WIB.820 Roger to be consulted about replacing two of the fence posts around the War Memorial that have rotted.

WIB.821 It was agreed that four new planters would be enough in the front of the Cricket Pavilion. There is spare wood on the allotment which can be used for these.

WIB.822 Work on the Gandy Field is ongoing. Angela is waiting for more slabs to be put in place and Jane volunteered to plant the wallflowers that are ready.

WIB.823 As touched on earlier. Simon Green is happy to provide the prizes for the competitions. Alan Sinclair has also offered to sponsor a planter. A contract must be produced by the Parish Council for this to happen. Once this has been done and the money received, a Sponsors Notice can be placed on the planter.

WIB.824 Business for next meeting. Draft copy of brochure available. Confirmation of entry to Village in bloom.